## Tasks
Term 2
TO DO
Task ID | Task Name | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Points Estimate | Points Estimate Rolled Up
86a6gh5vj | Release 1 | TO DO | For Release 1, our goal is to decide whats the project goals, requirement, deliverables, and scope of project. Decide together with Dot Foods to make sure we are on the same track | Damario Abdalla |  |  | 0 | 0 | 2025-02-21 |  | 2025-02-02 13:09 | 2025-02-17 15:55 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 | 86a6gh8ur 86a6gh6qv 86a6gh6u4 86a6gh6xw 86a6gh74x | https://app.clickup.com/t/86a6gh8ur https://app.clickup.com/t/86a6gh6qv https://app.clickup.com/t/86a6gh6u4 https://app.clickup.com/t/86a6gh6xw https://app.clickup.com/t/86a6gh74x |  | Term 2 | [8 empty] | 0
86a6gh8ur | Kick Off Meeting | COMPLETE | Meeting between the team with Dot Foods Team(Catherine Barr) | Damario Abdalla | NORMAL |  | 0 | 0 | 2025-01-31 |  | 2025-02-02 13:21 | 2025-02-17 15:41 |  | 2025-02-17 15:40 | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh6qv | Collect Data from Dot Foods | IN PROGRESS | Catherine is gathering the data and will hold a meeting for us at 20th February 2025 to explain it | Damario Abdalla, Haiyang Yuan | HIGH |  | 0 | 0 | 2025-02-20 |  | 2025-02-02 13:11 | 2025-02-17 15:43 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh6u4 | Meeting with team members on solutions for Catherine | PLANNING | Meeting to decide whats the next plan to solve Catherine problems | Damario Abdalla, Ziyuan Wang | NORMAL |  | 0 | 0 | 2025-02-24 |  | 2025-02-02 13:11 | 2025-02-17 15:43 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh6xw | Create a workflow on Draw.IO for DotFoods | PLANNING | Create a work flow to explain our thought process | Daniel McGhee | NORMAL |  | 0 | 0 | 2025-02-19 |  | 2025-02-02 13:12 | 2025-02-17 15:44 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh74x | Present workflow to Dot Foods | PLANNING | Present the workflow and solution to make sure Dot Foods is on board with out soltuion | Daniel McGhee | NORMAL |  | 0 | 0 | 2025-02-21 |  | 2025-02-02 13:13 | 2025-02-17 15:44 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh5w6 | Release 2 | TO DO | For release 2, our goal is to found insights on their data. Present the insights, and explain our next step to Dot Foods, knowing what the data is capable | Damario Abdalla |  |  | 0 | 0 | 2025-03-07 |  | 2025-02-02 13:09 | 2025-02-17 15:56 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 | 86a6gh7bb 86a6gh7d3 86a6gh7eu 86a6gh7u3 | https://app.clickup.com/t/86a6gh7bb https://app.clickup.com/t/86a6gh7d3 https://app.clickup.com/t/86a6gh7eu https://app.clickup.com/t/86a6gh7u3 |  | Term 2 | [8 empty] | 0
86a6gh7bb | Meeting for Dividing Task | TO DO | Meeting to decide everyones responsibilities to work faster | Damario Abdalla, Mrinali Dole | LOW |  | 0 | 0 | 2025-02-26 |  | 2025-02-02 13:14 | 2025-02-17 15:45 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh7d3 | Conduct EDA | TO DO | Conduct the EDA to find insights on Dot Foods Data for future presentation | Mrinali Dole, Jiahe Li | HIGH |  | 0 | 0 | 2025-03-03 |  | 2025-02-02 13:14 | 2025-02-17 15:46 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh7eu | Create a presentation for our EDA | TO DO | Create a presentation of our finding for them to clarify | Ziyuan Wang, puyuez2@illinois.edu | NORMAL |  | 0 | 0 | 2025-03-07 |  | 2025-02-02 13:14 | 2025-02-17 15:46 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh7u3 | Present Dot Foods our EDA | TO DO | Present our findings to make sure we are on the right path | puyuez2@illinois.edu, Ziyuan Wang | NORMAL |  | 0 | 0 | 2025-03-05 |  | 2025-02-02 13:16 | 2025-02-17 15:48 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh5wu | Release 3 | TO DO | For release 3, create a machine learning model that could solve Dot Foods problem using their Data | Damario Abdalla |  |  | 0 | 0 |  |  | 2025-02-02 13:09 | 2025-02-17 15:57 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 | 86a6gh7kw 86a6gh7r8 86a6gh7t3 86a6gh7u7 | https://app.clickup.com/t/86a6gh7kw https://app.clickup.com/t/86a6gh7r8 https://app.clickup.com/t/86a6gh7t3 https://app.clickup.com/t/86a6gh7u7 |  | Term 2 | [8 empty] | 0
86a6gh7kw | Create Machine learning Model for Customer Segmentation | TO DO | Create machine learning model to solve Dot Foods issue on customer segmentation | Mrinali Dole, Jiahe Li | NORMAL |  | 0 | 0 | 2025-03-12 |  | 2025-02-02 13:15 | 2025-02-17 15:48 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh7r8 | Create comparison model | TO DO | Compare models performance for us to select and present to the client | Jiahe Li, Mrinali Dole | LOW |  | 0 | 0 | 2025-03-18 |  | 2025-02-02 13:16 | 2025-02-17 15:49 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh7t3 | Create Presentation for Model | TO DO | Create a presentation explaining the model for dot foods | Haiyang Yuan, Jiahe Li | NORMAL |  | 0 | 0 | 2025-03-26 |  | 2025-02-02 13:16 | 2025-02-17 15:49 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh7u7 | Present Model to Dot Foods | TO DO | Present the model and explain the pros and cons of the model, use the one that Dot Foods is interested in using | Damario Abdalla, Haiyang Yuan, Jiahe Li | NORMAL |  | 0 | 0 | 2025-03-28 |  | 2025-02-02 13:16 | 2025-02-17 15:50 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh5x7 | Release 4 | TO DO | For release 4, integrate our machine learning to a dashboard so Dot Foods could use them and integrate it to their system | Damario Abdalla |  |  | 0 | 0 | 2025-04-21 |  | 2025-02-02 13:09 | 2025-02-17 15:58 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 | 86a6gh7xv 86a6gh7z2 86a6gh7zp 86a6gh89z | https://app.clickup.com/t/86a6gh7xv https://app.clickup.com/t/86a6gh7z2 https://app.clickup.com/t/86a6gh7zp https://app.clickup.com/t/86a6gh89z |  | Term 2 | [8 empty] | 0
86a6gh7xv | Meeting on What to Show on Dashboard | TO DO | Create a display for the machine learning, probably using a dashboard. Decide what to show on it | Damario Abdalla, Ziyuan Wang, Daniel McGhee | NORMAL |  | 0 | 0 | 2025-04-02 |  | 2025-02-02 13:16 | 2025-02-17 15:51 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh7z2 | Present to Dotfoods Our Dashboard Plan | TO DO | meeting with dot Foods to show our rough plan of the dashboard | Damario Abdalla, puyuez2@illinois.edu | NORMAL |  | 0 | 0 | 2025-04-09 |  | 2025-02-02 13:17 | 2025-02-17 15:51 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh7zp | Create Dashboard | TO DO | Create the dashboard that fits Dot Foods Requirement and Deliverable | Mrinali Dole, Ziyuan Wang | NORMAL |  | 0 | 0 | 2025-04-16 |  | 2025-02-02 13:17 | 2025-02-17 15:52 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh89z | Show Dashboard to Dot Foods(Catherine Barr) | TO DO | Present the Dashboard and explain how to use them | Mrinali Dole, Ziyuan Wang | NORMAL |  | 0 | 0 | 2025-04-18 |  | 2025-02-02 13:18 | 2025-02-17 15:52 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh5xm | Final Deliverables | TO DO | For release 5, create the documentation and presentation to explain everything that we did. This is to make sure we could publish our work or Dot Foods wants to improve our works by their own, they could use the documentation | Damario Abdalla |  |  | 0 | 0 |  |  | 2025-02-02 13:09 | 2025-02-17 15:59 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 | 86a6gh82d 86a6gh857 86a6gh876 | https://app.clickup.com/t/86a6gh82d https://app.clickup.com/t/86a6gh857 https://app.clickup.com/t/86a6gh876 |  | Term 2 | [8 empty] | 0
86a6gh82d | Create Presentation of All our Process | TO DO | Create presentation for final presentation that encapsulates our process | puyuez2@illinois.edu, Daniel McGhee | HIGH |  | 0 | 0 | 2025-04-23 |  | 2025-02-02 13:17 | 2025-02-17 15:53 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh857 | Create Documentation for Dashboard and Model | TO DO | Create documentation for Dot FOods for them to use our dashboard and model for future use | Haiyang Yuan, Jiahe Li | NORMAL |  | 0 | 0 | 2025-04-25 |  | 2025-02-02 13:18 | 2025-02-17 15:53 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0
86a6gh876 | Show Dashboard, Model, Documentation to Dot Foods | TO DO | Present all of our product to the class and Dot Foods | Damario Abdalla, puyuez2@illinois.edu | NORMAL |  | 0 | 0 | 2025-05-02 |  | 2025-02-02 13:18 | 2025-02-17 15:54 |  |  | Damario Abdalla | Spring Semester - Dot Foods | hidden | Term 2 |  |  |  | Term 2 | [8 empty] | 0